## Advanced Planning
Olam Tikvah Planning for HMV Program
2012-2013
Task | Committee | Assignee | Assistant | Due Date | Status
Develop theme of Jewish Role Model Series | Religious Education | Eric Rothberg | Steve Tursky | 2012-04-01 | Done
Put on Men's Club planning 2012/2013 calender, 3-session series | All |  |  | 2012-05-01 | Done
Discuss program with Rabbis, gain their support | Religious Education | Eric Rothberg | Steve Tursky | 2012-07-01 | Done
Send calender of upcoming events to all members | Communications | Bob Watts | Eric Rothberg | 2012-08-15 | Done
Include in synagogue monthly newsletter | Communications | Bob Watts | Eric Rothberg | 2012-10-15 | Done
Include in weekly Shabbat bulletin and listserv email | Communications | Bob Watts | Eric Rothberg | 2012-12-01 | Done
Include in Constant Contact email to all Club members | Communications | Bob Watts | Eric Rothberg | 2012-12-01 | Done
Email and approach in-person participants in past HMV | Religious Education | Eric Rothberg | Steve Tursky | 2013-12-10
Email and approach in-person participants new prospects | Religious Education | Eric Rothberg | Steve Tursky | 2012-12-10 | Done
Develop handouts for participants with questions | Religious Education | Eric Rothberg | Steve Tursky | 2012-12-20 | Done
Session 1 on Ethical Speech | Religious Education | Eric Rothberg | Steve Tursky | 2012-12-27 | Done
Review lessons learned at monthly Club meeting | All | Eric Rothberg | Steve Tursky | 2013-01-03 | Done
Develop handouts for participants with questions | Religious Education | Eric Rothberg | Steve Tursky | 2013-01-13 | Done
Session 2 on Juggling Responsibilities | Religious Education | Eric Rothberg | Steve Tursky | 2013-01-20 | Done
Review lessons learned at monthly Club meeting | All | Eric Rothberg | Steve Tursky | 2013-02-07 | Done
Develop handouts for participants with questions | Religious Education | Eric Rothberg | Steve Tursky | 2013-02-21 | Done
Session 3 on Ethics in Workplace | Religious Education | Eric Rothberg | Steve Tursky | 2013-02-28 | Done
Review lessons learned at monthly Club meeting | All | Eric Rothberg | Steve Tursky | 2013-03-07 | Done
.