## Sheet
Torch Award Program Schedule
As of Date
2020-06-06
Task | Assignee | Assistant | Due Date | Status
Planning
Creation of Idea | Alan |  | 2019-11-28 | Done
Connect with local food banks | Alan |  | December | Done
Coordinate with Shul for location for drop off | Alan |  | 2019-12-10 | Done
Coordinate with Maintence for items needed | Alan |  | 2019-12-10 | Done
Seek Volunteers | Alan |  | 2019-12-12 | Done
Publicity
Email Campaign to Temple and outreaching areas on Facebook | Alan |  | 2020-01-03 | Done
Multiple emails througout Janaury
Execution
Set up tables and space | Alan | Brenda | 2020-02-03 | Done
Collect food and sort as needed | Alan | Brenda | 2020-02-03 | Done
Deliver collection to Blessing Bag Brigade for their delivery | Alan |  | 2020-02-03 | Done