## Advanced Planning
Program Advanced Planning
Men's Club Shabbat 'Bar Mitzvah' Feb. 9, 2013
Task | Committee | Assignee | Assistant | Due Date | Status
Initial Planning
Discuss concept and general ideas of program at annual planning meeting during the summer | Men's Club Board | Men's Club Board |  | 7/16/12 | Complete
Identify 2 or 3 potential dates | Men's Club Board | Men's Club Board |  | 7/16/12 | Complete
Put on Temple Calendar | President | John S. |  | 7/31/12 | Complete
Determine potential Chairmen for the 4 committees | Men's Club Board | Men's Club Board |  | 7/16/12 | Complete
Ask potential chairman | President | John S. |  | 7/31/12 | Complete
Publicity
Formal Announce at Men's Club Congregational Breakfast | Publicity Comm. | John S. |  | 10/31/12 | Complete
Create Men's Club Shabbat 'Bar Mitzvah' Flyer | Publicity Comm. | John S. |  | 10/31/12 | Complete
Create Tribute Book Ad Flyer | Publicity Comm. | John S. |  | 10/31/12 | Complete
Post Flyers around Temple | Publicity Comm. | John S. |  | 12/2/12 | Complete
Mail Flyers to all Temple Members | Publicity Comm. | Publicity Comm. |  | 12/15/12 | Complete
eMail flyers to Men's Club Members | Publicity Comm. | John S. |  | 12/2/12 and 1/6/13 | Complete
Special article about event in Hakol (Temple Newsletter) | Publicity Comm. | Barry L. |  | December Issue | Complete
Info about program in monthly Hakol article | Publicity Comm. | Barry L. |  | December and January Issues | Complete
Advertise in Regional Constant Contact to invite members from other chapters in region. | Publicity Comm. | John S. |  | December email | Complete
Advertise in Shabbat Flyer | Publicity Comm. | Barry L. |  | Every week beginning 1/5/13 Shabbat | Complete
Arrange to put in weekly Temple constant contact | Publicity Comm. | Barry L. |  | Every week beginning 1/5/13 Shabbat | Complete
Arrange to have announced from Bimah on Shabbat | Publicity Comm. | David S. |  | Every Shabbat beginning 1/12/13 | Complete
Service Planning
Identify Roles (Changes year to year depending on the specific Shabbat) | Service Comm. | Dan Z./Ralph |  | 11/15/12 | Complete
Determine key people to have honors | Service Comm. | John S. |  | 12/1/12 | Complete
Coordinate with Rabbi/Cantor | Service Comm. | Dan Z. |  | 12/1/12 | Complete
Give out roles/manage process | Service Comm. | Dan Z. |  | 1/15/13 | Complete
Confirm participants | Service Comm. | Dan Z. |  | 1/31/13 | Complete
Give spreadsheet of roles/participants tp ushers/Rabbi/Cantor | Service Comm. | Dan Z. |  | 2/4/13 | Complete
Food Planning
Ask potential Temple Members to help prepare food | Food Comm. | Allen B. |  | 8/31/12 | Complete
Ask potential Temple Members to help prepare food | Food Comm. | Allen B. |  | 8/31/12 | Complete
Agree on menu | Food Comm. | Allen B./John S./Dahlia/Zvi |  | 12/15/12 | Complete
Agree on quantities | Food Comm. | Allen B./John S./Dahlia/Zvi |  | 1/15/13 | Complete
Identify people to setup | Food Comm. | Allen B. |  | 1/7/13 | Complete
Identify people to cleanup | Food Comm. | Allen B. |  | 1/7/13 | Complete
Fill out setup form for Temple office | Food Comm. | Allen B. |  | 1/31/13 | Complete
Buy food | Food Comm. | Dahlia/Zvi |  | 2/6/13 | Complete
Buy dishes/utensils/etc. | Food Comm. | JohnS./Joel P. |  | 2/6/13 | Complete
Buy flowers for centerpieces | Food Comm. | Allen B. |  | 2/8/13 | Complete
Cook Food | Food Comm. | Dahlia/Zvi |  | 2/8/13 | Complete
Setup Tables | Food Comm. | Setup volunteers |  | 2/8/13 | Complete
Tribute Book
Determine Ad prices | Men's Club Board | Men's Club Board |  | 10/1/12 | Complete
Find layout creater and printer | Tribute Book Comm. | David S. |  | 10/1/12 | Complete
Determine cutoff date | Tribute Book Comm. | David S. |  | 10/31/12 | Complete
Manage Ad finances | Tribute Book Comm. | John S |  | Duration | Complete
Determine coordinator w/creator | Tribute Book Comm. | David S. |  | 10/1/12 | Complete
Add Men's Club 'non-tribute' pages | Tribute Book Comm. | David S. |  | 1/8/13 | Complete
Coordinate w/Rabbi to write an intro | Tribute Book Comm. | David S. |  | 1/8/13 | Complete
Intro by Men's Club President | Tribute Book Comm. | John S |  | 1/8/13 | Complete
Proofread Book | Tribute Book Comm. | David S./John S. |  | 1/29/13 | Complete
Pickup Books | Tribute Book Comm. | David S. |  | 2/7/13 | Complete
Put out in lobby before service | Tribute Book Comm. | John S. |  | 2/8/13 | Complete
After Men's Club Shabbat
Donate Extra Food | Food | Allen |  | 2/11/13 | Complete
Write personal thank you notes to contributors to Tribute Book | President | John S |  | 3/1/13 | Complete
.

## Sample
Sample Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 3.1.2013 | Done
Add new committee member or two |  | Robert | Brian | 3.1.2013 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 3.15.2013 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 3.15.2013 | Done
Update website |  | Jacob |  | 3.1.2013 | Done
Produce Brochure | Publicity | Josh | Jim | 3.25.2013 | Done
Create press releases; articles | Publicity | Josh | Jim | 4.10.2013 | Done
Email Press Releases to newspapers |  | Josh |  | 4.15.2013 | Done
Update menus | Commisary | Jim |  | 4.25.2013 | Done
Get photographer |  | Joe |  | 4.30.2013 | Done
Phone-a-thon |  | Robert | Brian | 2.29.2013 | Open
Book Room |  | Bruce |  | 3.1.2013 | Done
Lessons Learned Meeting |  | all |  | 6.15.2013
Birkat booklets: Mark Druy |  | Elliot
Greeters Greg Kadinov |  | David
Buy Insurance |  | David
Camp staff person doing a greeting |  | Elliot | yes
People to Introduce speakers |  | Both
Cameraman for group pictures |  | David
Rent chairs for Sanctuary |  | Elliot | Lou
Schedule HMV sessions |  | Both
Recruit HMV facilitator |  | Both
Talk to Committee about where to hold sessions |  | Both
Compile survey |  | Both