## Explanation
Torch Award Program Schedule
North Shore Jewish Center Pancake Breakfast Planning
Task | Assignee | Date | Status
Enter event on NSJC Calendar | Jerry | Jun. 15 | Done
Update Flyer | Brian | Nov. 5 | Done
Ask for volunteers at MC meeting | Jeff | Nov.10 | Done
Send flyer to synagogue members weekly | Jeff | Nov. 11 | Done
Inventory supplies | Jim | Dec.1 | Done
Prepare shopping list | Jim | Dec.2 | Done
Shopping | Jim | Dec. 23 | Done
Prepare and set up | All | Dec. 25 | Done

## Sample 1
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Planning
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Book Room |  | Bruce |  | 2020-03-01 | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Publicity
Update website |  | Jacob |  | 2020-03-01 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Produce brochure or flyer | Publicity | Josh | Jim | 2020-03-25 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email press releases to newspapers |  | Josh |  | 2020-04-15 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Execution
Purchase menu items |  | Jim |  | 2020-06-01 | Done
Room set up |  | Bruce |  | 2020-06-03 | Done
Set out food |  | Jim |  | 2020-06-08
Welcome speaker |  | Joe |  | 2020-06-08
Welcome attendees |  | Josh | Robert | 2020-06-08
Lessons Learned Meeting |  | all |  | 2020-06-15

## Sample 2
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Update website |  | Jacob |  | 2020-03-01 | Done
Produce Brochure | Publicity | Josh | Jim | 2020-03-25 | Done
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email Press Releases to newspapers |  | Josh |  | 2020-04-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Book Room |  | Bruce |  | 2020-03-01 | Done
Lessons Learned Meeting |  | all |  | 2020-06-15