## Political Breakfast
Political Breakfast Planning Schedule
Date taking place: the Sunday morning prior to Election Day in November
Time: Doors typically open at 8:30am, event begins at 9:15am.
Task | Assignee | Assistant | Due Date | Comment
Planning
Reserve the date and ballroom at annual Synagogue calendar meeting | Club President | Club Vice President | Preceding May
Check what races are taking place in November | Harry | TBD | July
Check that club committee chairman are on board to continue in roles | Harry |  | August
Contact political clubs to remind them about the event and enlist their help in contacting the candidates | Murray |  | August
Contact candidates to enlist their participation in the Political Breakfast. | Murray |  | September until day of event
Kitchen Crew - discussion at club meeting on how many to expect at the breakfast. Plan on purchasing adequate amount of food. | Mark | Kitchen crew members | October
Submit room set-up instructions to synagogue executive director. | Club President |  | October
Raffle - Purchase books on Israel to raffle off. Prepare raffle supplies. | Andy |  | October
Check what candidates plan on attending. Draft agenda. | Harry, Murray |  | October
Plan questions to be asked | Harry |  | October
Check that club committee chairman are prepared for day of event | Club President, Harry |  | Last week in October
Publicity
Insert advertisement in monthy synagogue bulletin for Sept., Oct., and Nov. | Larry |  | August
Insert advertisement in weekly synagogue email | Larry |  | Mid-October
Check with local newpapers and television if they wish to attend | Larry |  | October
Execution
Purchase food items that still need to be purchased | Kitchen Crew |  | Week before
Check with exeutive director that room will be set up in accordance with instructions. | Club President |  | Week before
Check that dais and microphones are set up correctly | Harry | Bob | 7am day of event
Kitchen crew reports to synagogue | Kitchen Crew |  | 7am day of event
Set up tables and prepare food | Kitchen Crew |  | 7am day of event
Display raffle prizes. Start selling raffles. | Andy |  | 8:30am
Set out food | Kitchen Crew |  | Approx. 9am
Welcome candidates | Harry | Bob | As they arrive
Welcome attendees | Harry |  | 9:15am start
Help clean up after event | All club members |  | Post-event
Lessons Learned Meeting | Club President |  | Next club meeting

## Explanation
Torch Award Program Schedule
On the online application, we ask that you describe the timeline with all the tasks to make the program work. The timeline will explain: aspects of program advance planning, how long did it take, key events, how did your members participate. Describe this information on a spreadsheet such as the ones that follow and upload it to the online application.

## Sample 1
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Planning
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Book Room |  | Bruce |  | 2020-03-01 | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Publicity
Update website |  | Jacob |  | 2020-03-01 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Produce brochure or flyer | Publicity | Josh | Jim | 2020-03-25 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email press releases to newspapers |  | Josh |  | 2020-04-15 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Execution
Purchase menu items |  | Jim |  | 2020-06-01 | Done
Room set up |  | Bruce |  | 2020-06-03 | Done
Set out food |  | Jim |  | 2020-06-08
Welcome speaker |  | Joe |  | 2020-06-08
Welcome attendees |  | Josh | Robert | 2020-06-08
Lessons Learned Meeting |  | all |  | 2020-06-15

## Sample 2
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Update website |  | Jacob |  | 2020-03-01 | Done
Produce Brochure | Publicity | Josh | Jim | 2020-03-25 | Done
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email Press Releases to newspapers |  | Josh |  | 2020-04-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Book Room |  | Bruce |  | 2020-03-01 | Done
Lessons Learned Meeting |  | all |  | 2020-06-15