## Let's Get Cooking
Let' Get Cooking
As of Date
2020-01-17
Task | Assignee | Due Date | Status
Contact Hank about leading a class on Brisket making | Richard | 2019-11-05 | Done
Reserve Synagogue Social Hall for Event | Stewart | 2019-11-12 | Done
Build email list for event | Roger | 2019-11-12 | Done
Finalize Advertsing,c ost and price for event | Richard | 2019-11-13 | Done
Send out initial email to club members for event | Richard | 2019-11-14 | Done
Send Event Ad to Synagogue to publish in December 2019 bulletin | Richard | 2019-11-14 | Done
Add advertisement to Men's club website and payment option | Bruce | 2019-12-13 | Done
Send Event Ad to Synagogue to publish in January 2020 bulletin | Richard | 2019-12-14 | Done
Report on registrations | Bruce | 2019-12-27 | Done
Contact Hank to let him know how many briskets we need | Richard | 2019-12-27 | Done
Send out second email to club members for event | Richard | 2019-12-29 | Done
Report on registrations | Bruce | 2020-01-03 | Done
Contact Hank to with final brisket order | Richard | 2020-01-05 | Done
Check with Hank on delivery of Briskets to Synagogue Kitchen | Richard | 2020-01-07 | Done
Meet Hank at Synagogue for drop off of Briskets and supplies | Richard | 2020-01-09 | Done
Attend Event | Everyone | 2020-01-12 | Done
Collect Photos taken at event |  | 2020-01-13 | Done
Submit Brisket Bill to Treasurer for Payment | Dan | 2020-01-15 | Done
Discussed event at Board Meeting. Lessons Learned | Everyone | 2020-02-02 | Done