## Explanation
Torch Award Program Schedule
On the online application, we ask that you describe the timeline with all the tasks to make the program work. The timeline will explain: aspects of program advance planning, how long did it take, key events, how did your members participate. Describe this information on a spreadsheet such as the ones that follow and upload it to the online application.
For each Program:
Identify possible topics & speakers - through conversations at BH Board meetings and with individual members
Select a topic and obtain a speaker.
Chaim Blook contacted through a BH member related to him
I contacted Tamim Saad via Israeli Consulate (someone I know at the Consualte)
I worked with my contact at the Israeli Consualte to obtain the new Consul General as a speaker
Determine precise topic/subject matter to be discussed - through discussions with speaker & BH Board members & other BH members
Agree on date/time for the event and reserve Zoom account for the event.
Ask someone to be program moderator - R Lerner for Cahim Bloom, myself for Tamim Saad, R Lerner for Israeli CG, BH Member Adam Samansky for Cyber Security event next month
Work with staff person to develop flyer for publicity. Get agreement on this from speaker & BH President & sometimes the Rabbi.
Staff send out publicity during the two weeks prior to the event - dedicatied Email blasts, links & brief descriptions in general Temple communications.
Also, I post something on Emunah-Helps the week before the event.
BH President does the Zoom mechanics
I arrange for speaker and all involved to meet on line 15 minutes before the Zoom event starts.
Generally need to start this process about 2 months in advance.

## Sample 1
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Planning
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Book Room |  | Bruce |  | 2020-03-01 | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Publicity
Update website |  | Jacob |  | 2020-03-01 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Produce brochure or flyer | Publicity | Josh | Jim | 2020-03-25 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email press releases to newspapers |  | Josh |  | 2020-04-15 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Execution
Purchase menu items |  | Jim |  | 2020-06-01 | Done
Room set up |  | Bruce |  | 2020-06-03 | Done
Set out food |  | Jim |  | 2020-06-08
Welcome speaker |  | Joe |  | 2020-06-08
Welcome attendees |  | Josh | Robert | 2020-06-08
Lessons Learned Meeting |  | all |  | 2020-06-15

## Sample 2
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Update website |  | Jacob |  | 2020-03-01 | Done
Produce Brochure | Publicity | Josh | Jim | 2020-03-25 | Done
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email Press Releases to newspapers |  | Josh |  | 2020-04-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Book Room |  | Bruce |  | 2020-03-01 | Done
Lessons Learned Meeting |  | all |  | 2020-06-15