## Area Club
Area Club Schedule
Task
Planning
Have an initial meeting with key people in the community that can make this possible. At a minimum, 1 representative from each of the following groups: the Jewish Community Center / Local Federation, each conservative shul, each reform shul, each orthodox shul, each chabad, etc
Create a Club Bylaws detailing how the club is to be organized operationally and financially.
Get in touch with FJMC for information on affiliating.
Publicity
Advertise and gain members
Affiliating
Elect officers
Submit application for affiliation with FJMC
Next Steps
Create an events calendar
Continue to advertise the club and attract members

## Sample 1
Torch Award Program Schedule |  |  | (Sample items inserted)
As of Date
2020-06-06
Task |  | Assignee | Assistant | Due Date | Status
Planning
Update email list for latest committee (remove old members) |  | Jim |  | 2020-03-01 | Done
Add new committee member or two |  | Robert | Brian | 2020-03-01 | Done
Create budget | Finance | Bruce |  |  | Done
Book Room |  | Bruce |  | 2020-03-01 | Done
Speaker Topics | Speakers | Joe | Jim | 2020-03-15 | Done
Update menus | Commisary | Jim |  | 2020-04-25 | Done
Publicity
Update website |  | Jacob |  | 2020-03-01 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 2020-03-15 | Done
Produce brochure or flyer | Publicity | Josh | Jim | 2020-03-25 | Done
Phone-a-thon |  | Robert | Brian | 2020-03-28 | Open
Create press releases; articles | Publicity | Josh | Jim | 2020-04-10 | Done
Email press releases to newspapers |  | Josh |  | 2020-04-15 | Done
Get photographer |  | Joe |  | 2020-04-30 | Done
Execution
Purchase menu items |  | Jim |  | 2020-06-01 | Done
Room set up |  | Bruce |  | 2020-06-03 | Done
Set out food |  | Jim |  | 2020-06-08
Welcome speaker |  | Joe |  | 2020-06-08
Welcome attendees |  | Josh | Robert | 2020-06-08
Lessons Learned Meeting |  | all |  | 2020-06-15