## Advanced Planning
Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Create Committee |  | Phil | Marty | 9.25.2011 | done
Order Candles, boxes, bags | Board meeting | Marty |  | 10.1.2011 | done
Deadline for regional candle order |  |  |  | 12.31.2011 | done
Submit article to temple newesletter | Publicity | Phil |  | 1.2.2011 | done
Set date to box candles | Planning | Phil |  | 1.2.2013 | done
Ask Religious School address labels by class | Distribution | Marty |  | 2.14.2013 | done
Reminder in newsletter and Temple E-mail | Publicity | Phil |  | 2.17.2011 | done
Send Rabbi Letter First donation request 6 weeks | Planning | Marty |  | 3.6.2011 | done
Submit news Release to media | Publicity | Phil |  | 3.9.2011 | done
Put together packing team & publicity | Publicity | Phil |  | 3.10.2011 | done
Last day for Bulk Orders | Region |  |  | 3.16.2011 | done
Print donation letter for box insert 2nd request | Distribution | Marty |  | 3.18.2011 | done
Pring merge children into meditation | Distribution | Marty |  | 3.18.2011 | done
Candle Packing /MC Board Meeting | Distribution | Phil | Jacob | 3.20.2011 | done
Provide candles to Temple office for pick up |  |  |  | 3.20.2011 | done
Temple wide E-Mail to pick up or have delivered | Distribution | Marty |  | 3.21.2011 | done
Creat Distribution routes | Distribution | Marty |  | 3.20.2011 | done
Deliver candles March 25 -- April 1st | Distribution | Marty |  | 3.25.2011 | done
Announcement to Rabbi or Temple Pres to light | Planning | Phil |  | 3.30.2011 | done
Religious school brings home cnadles | Distribution | Marty |  | 4.1.2011 | done
Temple wide E-Mail reminder to light candles | Planning | Phil |  | 4.17.2011 | done
Light Yom HaShoah Candle |  |  |  | 4.18.2011 | done
Yom HaShoah |  |  |  | 4.19.2011 | done
Create spreadsheet of dist that have not donated |  |  |  | 5.20.2011 | done
Send 3rd donation request letter Shavout | Planning | Marty |  | 5.22.2011 | done
Do final accounting
.

## Sample
Sample Program Advanced Planning
Date
Task | Committee | Assignee | Assistant | Due Date | Status
Update email list for latest committee (remove old members) |  | Jim |  | 3.1.2013 | Done
Add new committee member or two |  | Robert | Brian | 3.1.2013 | Done
Create budget | Finance | Bruce |  |  | Done
Speaker Topics | Speakers | Joe | Jim | 3.15.2013 | Done
Email Save-the-Date to Temple Bulletins |  | Jacob |  | 3.15.2013 | Done
Update website |  | Jacob |  | 3.1.2013 | Done
Produce Brochure | Publicity | Josh | Jim | 3.25.2013 | Done
Create press releases; articles | Publicity | Josh | Jim | 4.10.2013 | Done
Email Press Releases to newspapers |  | Josh |  | 4.15.2013 | Done
Update menus | Commisary | Jim |  | 4.25.2013 | Done
Get photographer |  | Joe |  | 4.30.2013 | Done
Phone-a-thon |  | Robert | Brian | 2.29.2013 | Open
Book Room |  | Bruce |  | 3.1.2013 | Done
Lessons Learned Meeting |  | all |  | 6.15.2013
Birkat booklets: Mark Druy |  | Elliot
Greeters Greg Kadinov |  | David
Buy Insurance |  | David
Camp staff person doing a greeting |  | Elliot | yes
People to Introduce speakers |  | Both
Cameraman for group pictures |  | David
Rent chairs for Sanctuary |  | Elliot | Lou
Schedule HMV sessions |  | Both
Recruit HMV facilitator |  | Both
Talk to Committee about where to hold sessions |  | Both
Compile survey |  | Both